## Slide 1
Business Requirements Document (BRD) – AI-Powered eBook for Legislative Assemblies
Version Edition-2 (V2) – 11 August 2025

## Slide 2
Project Overview
Purpose: Enable rapid access and analysis of legislative documents
Target Users: Legislative assembly staff and researchers
Key Capabilities: AI summarization, sentiment analysis, PDF navigation, Q&A chatbot
Deliverables: Web platform with integrated AI services

## Slide 3
Project Objectives & Scope
Produce concise summaries for rapid understanding
Enable modern PDF navigation and search
Assess and label document sentiment/tone
Provide natural language Q&A with contextual answers

## Slide 4
Functional Requirements – Summary
AI-driven Summarization
PDF Flip & Scroll
Sentiment & Tone Analysis
Interactive Q&A Bot

## Slide 5
Non-Functional Requirements
Performance: Sub‑3‑second response
Security: Auth & role‑based permissions
Reliability: 99% uptime during sessions
Auditability: Log all user actions
Usability: Intuitive UI for non‑technical users

## Slide 6
Non-Functional Requirements (cont.)
Scalability: Easily onboard more users & documents

## Slide 7
Technology Stack
Backend: Python, FastAPI
Frontend: ReactJS, NextJS
AI/ML: TensorFlow, Hugging Face Transformers, GPT
Database: PostgreSQL
Deployment: Azure cloud

## Slide 8
Resource Allocation – Roles & Costs
AI Developer – 2 persons, 3 months
Frontend Developer – 1 person, 3 months
Backend Developer – 1 person, 3 months
Project Manager – 1 person, 3 months
UI/UX Designer – 1 person, 1 month

## Slide 9
Resource Allocation – Additional Roles
DevOps Engineer – 1 person, 1 month
Tester – 1 person, 2 months
Contingency – Tools & buffer

## Slide 10
Milestones Timeline
Requirement Analysis & UI/UX – Days 1–5
Core Development – Days 6–30
Integration & Test – Days 31–45
Deployment & Handover – Days 46–60

## Slide 11
Support & Additional Considerations
14 months post‑launch bug‑fix support
Hosting on Azure or equivalent
Payment terms: 20% start, 40% after dev, 30% post‑UAT, 10% post‑handover

## Slide 12
Document Version History
Version 2.0 – 2025-08-11 – Keerthika mathi – Edition–2 (V2)

## Slide 13
Thank You
Questions & Discussion